## Sheet1
Risk Identification and Analysis
Risk | Probability | Impact | Risk Exposure
Under-resourcing | 0.9 | 10000 | 9000
Lack of Funding | 0.8 | 10000 | 8000
Scheduling Errors | 0.8 | 12000 | 9600
Lack of Communicaiton | 0.75 | 10000 | 7500
Lack of Software Expierence | 0.75 | 10000 | 7500
Delayed Software | 0.6 | 25000 | 15000
Scope Creep | 0.6 | 25000 | 15000
Added Workload | 0.6 | 25000 | 15000
Lack of communicaiton | 0.55 | 15000 | 8250
Inadequate testing | 0.55 | 15000 | 8250
Poor Management/Loss of Management | 0.5 | 50000 | 25000
Low Customer Satisfaction | 0.4 | 40000 | 16000
Loss of Good Reputation | 0.3 | 40000 | 4000
Loss of staff | 0.3 | 100000 | 30000
Stakeholder Delays Project | 0.25 | 50000 | 12500
Unresolved Conflicts | 0.2 | 10000 | 2000
Product Design Failure | 0.15 | 100000 | 15000
Loss of Hardware due to Natural Events | 0.15 | 100000 | 15000
Hardware failure | 0.1 | 100000 | 10000